## Sheet1
Defect ID | Title | Severity | Priority | Status | Module | Test Case ID | Steps to Reproduce | Expected Result | Actual Result | Root Cause | Fix Applied(Simulated) | Retest Result | Date Logged | Date Closed
BUG-001 | Program accepts invalid ID inputs whereby the months are allowed to exceed 12 | High | P1 | Fixed | Validation Library | TC-BEMS-VALIDLIB-20 | Navigate to an ID field, and enter | The application should reject the input and display an error message | The application accepts the input | Program incorreclty allows 13 to pass the validation check | The IsValidSouthAfricanIdNumber() method was updated to check less than or equal to 12 | Pass | 06/07/2026 | 07/07/2026
BUG-002 | Program incorrectly validates the max allowed currency amount boundary | High | P2 | Fixed | Validation Library | TC-BEMS-VALIDLIB-17 | Navigate to a field that accepts an amount, and enter 999999,99 to trigger the validation check | The application should reject the input and display an error message | The method rejects the 999999.99 value. But isValidAmount() is never used in the application | The method uses < (less than) instead of <= (less than or equal to) Note: this methos was also nevber coded into the app | The conditional operator was changed to <=, and the isValidAmount() method was integrated into the app | Pass | 06/07/2026 | 07/07/2026
BUG-003 | Simple interest is calculated incorrectly | Critical | P1 | Fixed | Interest Calculator | TC-BEMS-INTEREST-01 | Calculate simple interest on a specific value | The program should return a value that is matyhematically correct | The program returns a value that is mathematically incorrect | When the system calculates the monthly rate, it devides by 10 instead of 12 | The formula has been updated | Pass | 06/07/2026 | 07/07/2026
BUG-004 | System returns a future value based on compund interest regardless of whether the user requests simple interest | High | P2 | Fixed | Interest Calculator | TC-BEMS-INTEREST-19 | Calculate a future value, and select simple interest | The program should calculate the future value based on simple interest | The program calculates the future value based on compounding interest regardless of whether the user requests simple interest to be used | The FutureValue() methods if (isCompound) else branch incorrectly calls CompoundInterest instead of SimpleInterest | The else branch in the FutureValue method has been fixed | Pass | 06/07/2026 | 07/07/2026
BUG-005 | Daily withdrawal limit is set to the amount the user initially deposits | High | P1 | Fixed | Account Management | TC-BEMS-ACC-24 | Create a new account, deposit a low initial balance for R350, attempt to withdraw R400, which is above the deposit limit, but below the withdrawal limit | The program should allow the user to make the withdrawal | The program does not allow the withdrawal to take place, as the withdrawal limit is incorrect | The initial deposit was incorrectly set as daily withdrawal limiit | A method was put in place to prompt the user to enter a daily withdrawal limit upon creating the account | Pass | 06/07/2026 | 07/07/2026
BUG-006 | The program allows an account with debt to be closed | Critical | P1 | Fixed | Account Management | TC-BEMS-ACC-25 | Create an account, take a loan out on the account, close the account | The program should not allow the account to be closed as it is in debt | The program incorrectly closes the account | The applicatrion source code incorrectly checks for Balance > 0, instead of !=0 | The Method was updated with !=0 | Pass | 06/07/2026 | 07/07/2026
BUG-007 | System allows exact full balance to be withdrawn from the account | Medium | P3 | Fixed | Transaction Engine | TC-BEMS-TRANS-22 | Withdraw the exact balance amount from the account | The program should reject the withdrawal | The system incorrecly approves the withdrawal allowing the account balance to be 0 | The program logic incorrectly uses < for the insufficient funds logic instead of <= | The logic was updated | Pass | 06/07/2026 | 07/07/2026
BUG-008 | Daily withdrawal limit is never reset | High | P2 | Fixed | Transaction Engine | TC-BEMS-TRANS-22 | Withdraw daily allowed limit, wait a day, attempt to make a withdrawal | The program should allow the user to make the withdrawal, as the limit has been reset | The program does not allow the withdrawal to happen as the limit was never resey | The daily withdrawal limit is never reset, and keeps on adding up | The withdrawal method logic was updated to reset the daily limit if the last withdrawal was made a day before the exact time of checking | Pass | 06/07/2026 | 07/07/2026
BUG-009 | System allows transfers to me made to closed or dormant accounts | Critical | P1 | Fixed | Transaction Engine | TC-BEMS-TRANS-30 | Set an account as dormant or closed and attempt to make a transfer | The program should not allow the transfer to happen as the destination account is closed | The program completes the transfer. | The program does not check whether the destination account is active | The transfer method was updated to check the account status of the destination accounts | Pass | 06/07/2026 | 07/07/2026
BUG-010 | DTI is incorrectly calculated by not including monthly installment in the calculation | High | P1 | Fixed | Loan Processing | TC-BEMS-LOAN-25 | Apply for a loan that will push monthly debt over the allowed limit | The system should not allow the loan to be approved | The program approves the loan, as it does not calculate the new installement into the userrs DTI | The program uses a faulty equation to calculate the DTI | The equation was updated to include the new monthly installment | Pass | 06/07/2026 | 07/07/2026
BUG-011 | The applicaion puts the account into a negative when making a loan repayment exceeding the value of the loan | Medium | P3 | Fixed | Loan Processing | TC-BEMS-LOAN-32 | Create a loan on an account, submit a repayment value of more than the amount of the loan | The loan should go away, and the user should have credit | The program incorrectly puts the account into a negative | The program incorrectly minuses the full repayment amount from the value of the loan | Method updated to check: if (amount > loan.OutstandingBalance) amount = loan.OutstandingBalance; | Pass | 06/07/2026 | 07/07/2026
BUG-012 | Settlement fee is calciulated on the principal amount instead of the outstanding loan balance | Critical | P1 | Fixed | Loan Processing | TC-BEMS-LOAN-33 | Calculate the settlement of a loan that is almost paid off | The fee should be calculated as a settlement percentage of the outstanding amount | The fee is correctly calculated as a percentage of the principal amount | The program incorrectly uses the principal amount in the settlement calculation | The calculation was updated to use the outstanding balance instead of the principal amount | Pass | 06/07/2026 | 07/07/2026
BUG-013 | The application does not allow a locked account to log back in, even after the lockoutExpiry time has expired | Medium | P2 | Fixed | Authentication | TC-BEMS-AUTH-19 | Lock an account by entering invalid credentials, and wait for logout expiry time to pass | The program should allow the user to attempt login after the timer has expired | The program never allows the user to log back in, even if the logout timeperiod has passed | The program never checks whether the lockout expiry time has expired | The Login method was updated to check whether the lockout expiry time has passed | Pass | 06/07/2026 | 07/07/2026
BUG-014 | Logged out sessions pass validation | Critical | P1 | Fixed | Authentication | TC-BEMS-AUTH-20 | Login to a session, wait for session token to expire, then perform action | The application should require reauthentication to make the session active again | The session never expires and remains active | The program never checks the activity of sessions | A the validate method was updated to check whether the session is active or not | Pass | 06/07/2026 | 07/07/2026
BUG-015 | The program still allows operations even though the session owner lacks permission | Critical | P1 | Fixed | Authentication | TC-BEMS-AUTH-21 | Login as admin, change users to lesser priviledged | The program should not allow the permissions to remain the same | The user remains to have permission, as long as the session is not ended | The application does not check whether the session is active or expired before granting permission | Added a method to check session activity before granting permission | Pass | 06/07/2026 | 07/07/2026
BUG-016 | Program allows users to generates reports for dates that have not passed yet | Low | P4 | Fixed | Reporting Engine | TC-BEMS-REPORT-06 | When generating a report, enter dates in the future | The program should not allow the user to generate a report as there is no data yet | The program accepts the dates and generates a report | The program does not check whether dates have passed before generating a report | Add a method to check whether the dates have passed before generating a report | Pass | 06/07/2026 | 07/07/2026
BUG-017 | The program accepts any date year, even if in the pass | Low | P4 | Fixed | Validation Library | TC-BEMS-VALIDLIB-19 | Navigate to a field that accepts an date, and enter 0091-01-01 | The application should reject the date | The application accepts the input | The app does not validate wether the year entered is valid | A method was implemented to validate the year of the date | Pass | 06/07/2026 | 07/07/2026