## Sheet1
Risk ID | Risk Description | Category | Likelihood (H/M/L) | Impact (H/M/L) | Risk Rating | Mitigation Strategy | Owner
R001 | Financial calculation errors in interest module | Functional | High | High | Critical | Boundary value tests + formula verification | Tester
R002 | Session token not invalidated on logout | Security | Medium | High | High | Auth test cases + manual trace | Tester
R003 | Able to transfer money to an account that does not exist, or one which is closed | Functional | Low | High | Medium | Design test cases that verify account status checks | Tester
R004 | Negative values are accepted when making a deposit | Functional | Medium | High | High | Ensure to make use of equivalence partitioning to test negative input partitions | Tester
R005 | Application throws exceptions that are not handled when null or empty fields are detected | Functional | Medium | Medium | Medium | Check all fields for empty, null, or whitespace fields. | Tester
R006 | Tellers are able to access admin-role only functions | Security | Medium | High | High | Implement role-based access control. Test RBAC for all user types | Tester
R007 | 1000 sequential transactions exceed acceptable amount of time to process | Performance | Medium | Medium | High | Use the C# builtin stopwatch feature when running test scripts to measure execution time | Tester
R008 | System freezes when generating a 12-month account statement for an account with 5000+ transactions | Performance | High | Medium | Medium | Use Nunit testing and implement the [Timeout] attribute to enforce performance SLA's | Tester
R009 | Passwords are stored as plain text in program code | Security | Low | High | High | Test password hashing enforcement. | Tester
R010 | SQL injection strings and/or special characters crash the program | Robustness | High | High | Critical | Upon testing, ensure to insert known strings that are malicious as input parameters. | Tester